# Project Charter Template

| PROJECT NAME |  | PROJECT MANAGERS | Team Name |
| --- | --- | --- | --- |
| Pet Adoption Awareness Initiative |  | Papa Arhin, Harjeet Kaur, Harshkumar Patel | Pawsitive Impact |

PROJECT OVERVIEW

| PROBLEM OR ISSUE | Although numerous animal shelters operate locally, many residents remain unaware of adoption opportunities or hold negative perceptions about shelter animals. This results in overcrowding, increased operational costs, and potential euthanasia for unadopted animals. The gap in public awareness limits adoption rates and prevents effective community engagement. |
| --- | --- |
| PURPOSE OF PROJECT | The purpose of this initiative is to design and implement a comprehensive awareness and education campaign that promotes pet adoption, connects shelters with potential adopters, and cultivates responsible pet ownership. The project seeks to improve knowledge, attitudes, and behaviors toward shelter animals. |
| BUSINESS CASE | Improved adoption outcomes generate significant social and economic benefits. Enhanced adoption rates: - Reduce shelter overcrowding - Lower municipal animal management costs - Improve community well-being through increased human–animal bonding The initiative is projected to increase adoption inquiries by 20–30% in six months, resulting in a 3–6-month payback period through cost avoidance and increased community participation. Long-term value includes strengthened animal welfare ethics and sustainable community engagement. |
| GOALS / METRICS | - Increase public awareness by 30%, measured through event participation and digital engagement. - Increase shelter adoption rates by 20% within the project period. - Educate 200+ community members on responsible pet ownership. - Establish 3–5 partnerships with shelters, veterinary clinics, and community groups. - Produce and distribute a full suite of educational materials (print & digital). |
| EXPECTED DELIVERABLES | - Increase public awareness by 30%, measured through event participation and digital engagement. - Increase shelter adoption rates by 20% within the project period. - Educate 200+ community members on responsible pet ownership. - Establish 3–5 partnerships with shelters, veterinary clinics, and community groups. - Produce and distribute a full suite of educational materials (print & digital). |

PROJECT SCOPE

| WITHIN SCOPE | - Design, development, and distribution of promotional materials - Collaboration with animal shelters and welfare groups - Execution of events and awareness activities - Public education on responsible pet care - Data collection and project impact evaluation |
| --- | --- |
| OUTSIDE OF SCOPE | - Veterinary or rescue services - Funding adoption fees - Creating long-term digital adoption tracking systems |

TENTATIVE SCHEDULE

| KEY MILESTONE (note these are examples below and you can choose to put in whatever you like from a Milestone basis) | START | FINISH |
| --- | --- | --- |
| Team Formation & Scoping | Nov 10, 2025 | Nov 13, 2025 |
| Charter Finalization and Kick-Off | Nov 14, 2025 | Nov 18, 2025 |
| Planning and Design | Nov 19, 2025 | Nov 28, 2025 |
| Implementation / Execution | Nov 29, 2025 | Dec 24, 2025 |
| Evaluation and Close-Out | Dec 25, 2025 | Jan 3, 2026 |

RESOURCES

| PROJECT TEAM | - Project Manager: Oversees planning, scheduling, stakeholder communication; ensures quality & timelines. - Communications & Outreach Lead: Designs awareness materials, leads social media campaigns, manages partnerships. - Research & Evaluation Analyst: Manages data collection, project evaluation, and continuous improvement insights. |
| --- | --- |
| SUPPORT RESOURCES | - Local shelters, veterinary clinics - Municipal animal services - Media channels and PR networks - Digital communication apps and design tools - Volunteer networks |
| SPECIAL NEEDS | - Access to adoption/shelter databases - Approval for community event spaces - Sponsorships or donations |

COSTS

| COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Labor – Project Planning and Coordination | Project Manager |  | $52/hr | 20 hrs | $1,040 |
| Labor – Campaign Design and Communications Development | Communications Lead |  | $45/hr | 20 hrs | $900 |
| Labor – Research, Data Analysis, and Evaluation | Research Analyst |  | $42/hr | 12 hrs | $504 |
| Supplies – Printing of Flyers, Brochures, and Educational Materials | Local Printer |  | $0.50/unit | 500 | $250 |
| Supplies – Design and Production of Promotional Posters and Banners | Print Vendor |  | $75/item | 3 | $225 |
| Event Logistics – Venue Booking, Setup, and Refreshments for Awareness Event | Community Center / Caterer |  | Flat Rate | 1 | $300 |
| Miscellaneous – Digital Marketing and Social Media Advertising | Meta Ads (Facebook/Instagram) |  | $20/day | 10 days | $200 |
|  |  |  | TOTAL COSTS |  | $3,419 |

| TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Specific Cost Savings | Cost savings from reduced shelter overcrowding |  |  |  | $3,300 |
| Enhanced Revenues | Sponsorships/donations |  |  |  | $1500 |
| Improved Compliance | Improved compliance with animal welfare standards |  |  |  | Qualitative Benefit |
| Improved Community Awareness | Enhanced community knowledge |  |  |  | Qualitative Benefit |
| Stronger Partnerships | Stronger shelter–community collaboration |  |  |  | Qualitative Benefit |
| Other Costs Avoided | Better decision-making based on collected data |  |  |  | Qualitative Benefit |
| Summary | Combined total of all quantified benefits (cost savings and sponsorships) and the aggregated value of qualitative improvements including compliance, community awareness, stronger partnerships, and enhanced decision-making. |  |  |  | $4,800 + all Quantitative benefits |
|  |  |  | TOTAL QUANTITATIVE BENEFIT |  | ≈ $4,800 |

Financial Summary / Business Case

| Payback Period, | 3.5 months |
| --- | --- |
| Net Present Value (NPV) | $1,381 |
| Benefit-Cost Ratio | 1.40:1 |
| Non-financial Considerations | Beyond financial performance, the initiative generates meaningful social, ethical, and environmental value. These include improved animal welfare, greater public understanding of responsible pet ownership, stronger partnerships among community stakeholders, and reduced shelter overcrowding. The initiative also promotes social responsibility and sustainability, supporting long-term community well-being and aligning with Sustainable Development Goal (SDG) 15 – Life on Land. |

RISKS, CONSTRAINTS, AND ASSUMPTIONS

| RISKS | • Low community engagement • Limited campaign budget • Event logistics failures • Social media misinformation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CONSTRAINTS | • Limited project timeframe • Dependence on external partners • Academic submission deadlines |  |  |  |  |  |
| ASSUMPTIONS | • Community shows interest in welfare issues. • Partners cooperate and share data • Approvals for venues and data collection granted promptly |  |  |  |  |  |
| PREPARED BY |  | TITLE |  |  |  | DATE |
| Papa Arhin Harjeet Kaur Harshkumar Patel |  | Project Manager Communications and Outreach Lead Research & Evaluation Analyst |  |  |  |  |